## Short Test Plan
Project: "WALLET" https://wallet-q-a.netlify.app/ |  | Introduction: | The Expense and Income Tracking Web Applications with statistic function and exchange rate table
Start date: | 2023-02-27 | Objective: | Providing timely and relevant feedback on the project to all interested parties within the framework of quality criteria: functionality, reliability, practicality, and efficiency...
End date: | 2023-03-05 | Principles: | Participation of the whole team, spreading quality ideas to the whole team
In Scope |  | Definition of Ready |  | Testing Team "Bug Hunters"
1 | Review | 1 | Technical Documentation is created | 1 | Team Lead | Zinaida Liashenko
2 | Functional testing | 2 | Web Application layout is created | 2 | Scrum Master | Yevgen Potoplyak
3 | Usability testing | 3 | Swagger documentation is completed | 3 | Manual Test Engineer | Marian Dolhyi
4 | UI testing | Definition of Done |  | 4 | Manual Test Engineer | Mykola Galych
5 | API testing | 1 | Technical Documentation has been reviewed | 5 | Manual Test Engineer | Iryna Kaniuk
6 | Security testing | 2 | Web Application layout has been checked | 6 | Manual Test Engineer | Vadym Lapin
7 | Localization testing | 3 | All checks according to the checklists have been provided | 7 | Manual Test Engineer | Svitlana Kiryanova
8 | Adhoc testing | 4 | The results of checks have been documented | 8 | Manual Test Engineer | Oksana Maksymchenko
9 | Compatibility testing | 5 | The Test Report has been generated | Timescales
Out of Scope |  | 6 | The Presentation has been finished | 1 | Planning | 1 day
1 | Unit testing | Test Environment |  | 2 | Monitoring and Control | 6 days
2 | Regression testing | 1 | Web browser: Google Chrome | 3 | Test Analysis | 1 day
3 | Performance testing | 2 | Devices: Laptop, Tablet, Mobile | 4 | Test Design | 1 day
Risks |  |  |  | 5 | Test Execution | 4 days
1 | Incorrect time estimation |  |  | 6 | Test Completion | 1 day
2 | Illness of one of the participants
3 | Lack of light

## High-level Checklist
Review | Documentation testing
Functional testing | Correctness of internal links.
Checking fields and pages "Registration"
Validation of "Authorization" fields and pages
Correct display of header elements and modal window for exiting the program
Correct display of main page elements for the first and other logins
Correctness of the modal window for adding a new transaction
Checking the addition and cancellation of the "Income" transaction (checking the fields, calendar, closing methods)
Checking the addition and cancellation of the "Expenditure" transaction (checking the fields, calendar, closing methods)
Validation of editing of existing transactions
The correctness of displaying the elements of the "Statistics" page
Checking the display of statistics
Check statistics chart
Checking the exchange rate
Usability testing | Navigation testing - we check the comprehensibility of pages, buttons, fields, whether the main page and menu are accessible from all other pages.
Content testing - we check the presence of grammatical errors, the size and quality of pictures, whether all headings are placed correctly.
Ease of use - we evaluate the clarity of the website structure and whether there are redundant components (all pages are checked).
UI testing | The overall appearance of the page: here the integrity of the appearance is checked (a rather subjective but important criterion), how harmonious and pleasant the software product looks, and it is also important to make sure that nothing is broken when scaling. Users can open pages of different devices with different permissions, it is important that on any of them the text is readable, all elements are displayed correctly, do not run into each other and do not disappear, and so on.
Text: There is always text on any page, and it should be given due attention when testing. Firstly, it should not contain errors, typographical errors and other possible errors. Secondly, the text should be aligned according to the same parameters so that the overall picture looks coherent and harmonious. It is also important to make sure how readable the text is when the page is scaled.
Element Selection : There are always elements on the page that the user can interact with. These elements should be highlighted in a certain way. Example: on a computer, when you hover over an interactive object, it lights up, or when you hover over a link, a window with additional information appears. There may be many options, but each of them requires verification. It is also important to make sure that when you click on a certain element, it is highlighted. This is important so that the user knows which option has been selected or which element is involved.
Working with fields: there are two types of fields - one is always unchanged, the other is intended for entering information. It is very important that these two types are clearly distinguished from each other so that the user cannot confuse or mistake them. But at the same time, all fields of the same type must be unified so that the design is in the same style.
Forms: When working with forms, there are many elements to pay attention to. First, this is the form window itself, its location, appearance, and so on. Second, the elements on the form: radio buttons, checkboxes, drop-down lists, text fields, and so on. All items must meet requirements and specifications.
Uniform look and feel : For the integrity of the interface, it is very important to unify the entire design. Colors, fonts, fields, icons, images and other elements on the pages of the software product must be standard for this project. After all, if something in the design stands out from the overall picture, it can affect the attitude of users towards the software product.
API testing | API testing
Security testing | We test that if the login and password are entered incorrectly, the user is not allowed into the system.
We are testing the automatic termination of session verification after a long period of user inactivity.
Localization testing | We test the correctness and completeness of the translation of the site's content into English
Adhoc testing | We test without preparation
Compatibility testing | We test the interface on a smartphone, tablet, computer
Тестування верстки | correct display of main blocks;
Markup testing | compliance with the approved layout;
the possibility of using different scales by the user without distorting the image;
the correctness of displaying the translation;
availability of clickable elements (links, buttons, icons, etc.);
highlight hints where provided;
availability of captions to images when they are disabled;
correct display of blocks when text is entered into them;

## Team
1 | Team Lead | Зіна | Zinaida Liashenko | liashenkozina@gmail.com | Correct display of header elements and modal window for exiting the program
Review of requirements
Test plan
2 | Scrum Master | Євген | Yevgen Potoplyak | lviv.radio@gmail.com | Check statistics chart
API
3 | Manual Test Engineer | Мар'ян | Marian Dolhyi | dolgy97@gmail.com | The correctness of displaying the elements of the "Statistics" page
Checking the display of statistics
4 | Manual Test Engineer | Микола | Mykola Galych | nng.post@gmail.com | Checking fields and pages "Registration"
Correctness of the modal window for adding a new transaction
5 | Manual Test Engineer | Ірина | Iryna Kaniuk | iryna1kaniuk@gmail.com | Checking the addition and cancellation of an "Expenditure" transaction
Checking the exchange rate
6 | Manual Test Engineer | Вадим | Vadym Lapin | lapinvadym789@gmail.com | Checking the addition and cancellation of the "Income" transaction
Checking the layout on the computer
Checking the layout on a tablet
7 | Manual Test Engineer | Світлана | Svitlana Kiryanova | kiryanovasv@gmail.com | Correct display of main page elements for the first and other logins
Checking the layout on the phone
8 | Manual Test Engineer | Оксана | Oksana Maksymchenko | mxeena84@gmail.com | Validation of "Authorization" fields and pages
Validation of editing of existing transactions

## TChecklist
ID | Check | Status (passed/failed) | Comments (test data)
Account
2023-01-01 | Register a new user | passed
2023-02-01 | Sign in with existing account | failed
2023-03-01 | Create a channel | blocked
2023-04-01 | Join channel
2023-05-01 | Add people to channel
2023-06-01 | Leave channel
Messages
2023-01-02 | Send dirrect message
2023-02-02 | Send message to a channel
2023-03-02 | Edit message
2023-04-02 | Delete message
...
...

## TTest case
ID | Target Description:
Type |  | Priority:
Pre-conditions:
1
2
Steps
Step |  | Expected result |  | Pass | Fail | Bug report ID
1
2
3
4
5
6
7
Executor: |  |  | Date:

## TBug Report
ID | #1
Reporter: |  | Assignee: | Status:
Type: |  | Severity: | Priority:
Browser: |  | OS: | OS version
Summary:
Description:
Pre-conditions:
1
2
Steps to reproduce:
1
2
3
4
Actual result:
Expected result:
Attachments:
Additional info: